## Sheet1
Domain Walkthrough | Design | Design Inspection | Code | Code Inspection | Promote to Build
1% | 40% | 3% | 45% | 10% | 1%
Domain Walkthrough & Plan | Code | Testing, Refactoring & Fixes | Update high-level design & Re-generate low-level design
1% | 50% | 40% | 9%
[6 empty] | Feature Set | feature | Domain Walkthrough & Plan |  | Code |  | Testing, Refactoring & Fixes |  | Update & Generate design |  | Notes
[8 empty] | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
[6 empty] | f1/staff_login | Login form for staff with authentication through use of LDAP server via python LDAP API | 2019-02-20 | 2019-02-20 | 2019-02-24 | 2019-02-26 | 2019-02-27 | 2019-02-01 | 2019-02-27 | 2019-02-01 | Behind because still getting used to project development process.
[6 empty] | f1/staff_login | I18n with Welsh localisation | N/A | 2019-03-01 | N/A | 2019-03-01 | N/A | 2019-03-01 | N/A | 2019-03-01 | This was an unplanned feature
[6 empty] | f2/history_management | List & delete any/all previous sessions | 2019-03-03 |  | 2019-03-03 |  | 2019-03-03 |  | 2019-03-03
[6 empty] | f2/history_management | View/Delete the questions of a session | 2019-03-04 |  | 2019-03-04 |  | 2019-03-04 |  | 2019-03-04
[6 empty] | f2/history_management | View & Edit each previous session meta-data | 2019-03-04 |  | 2019-03-04 |  | 2019-03-04 |  | 2019-03-04
[6 empty] | f2/history_management | Search the list/category of sessions for a session with a specific title or date | 2019-03-05 |  | 2019-03-05 |  | 2019-03-05 |  | 2019-03-05
[6 empty] | f2/history_management | Graphically display the feedback of a session | 2019-03-06 |  | 2019-03-06 |  | 2019-03-06 |  | 2019-03-06
Note on J7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Design is emerging from the refactorings. It is being generated from the code at the end. With changes made to the hogh-level design by hand if needed.
Note on W14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Design is emerging from the refactorings. It is being generated from the code at the end. With changes made to the hogh-level design by hand if needed.